## Sheet1
CSE325-Software Engineering Project
12BCE0501 & 12BCE0503
Project Plan |  | Requirement Document |  | Design Module |  | Basic Application Design
Start Date: 30-01-15 | S.No: 1 | Start Date: 04-02-15 | S.No: 2 | Start Date: 12-02-15 | S.No: 3 | Start Date: 25-02-15 | S.No: 4
End Date: 03-02-15 | Duration: 5 | End Date: 11-02-15 | Duration: 8 | End Date: 24-02-15 | Duration: 13 | End Date: 24-03-15 | Duration: 27
Advance Application Design
[6 empty] | Start Date: 25-03-15 | S.No: 5
[6 empty] | End Date: 20-04-15 | Duration: 26
|  |  |  | Bug Fixes and Final Documentation |  | Testing
|  |  |  | Start Date: 24-04-15 | S.No: 7 | Start Date: 21-04-15 | S.No: 6
|  |  |  | End Date: 30-04-15 | Duration: 7 | End Date: 23-04-15 | Duration: 3